## User Stories
ID | Story Title | Points | Priority | As a/an [user] | I want [functionality] | So that [value] | User Story | NFR | Definition of Done / Blockers | Epic ID | Status | Notes
A1 | Adult Registration | 2 |  | Adult | to register myself and my kid | my kid can participate in teens sports league. | As a/an Adult, I want to register myself and my kid, so that my kid can participate in teens sports league.
L2 | Team Manager Assignment | 1 |  | League Admin | to assign team manager roles to some adults | team manager can manage their team. | As a/an League Admin, I want to assign team manager roles to some adults, so that team manager can manage their team.
M3 | Team Creation | 1 |  | Team Manager | to create a new team | I can organize players in my team. | As a/an Team Manager, I want to create a new team, so that I can organize players in my team.
M5 | Invite Minors | 1 |  | Team Manager | to send invitations to registered minors to join my team | I can build my team. | As a/an Team Manager, I want to send invitations to registered minors to join my team, so that I can build my team.
A6 | Team Invitation | 1 |  | Adult | to accept or deny team invitations for my child | I control which team my child participates in. | As a/an Adult, I want to accept or deny team invitations for my child, so that I control which team my child participates in.
L7 | Minor Reassignment | 3 |  | League Admin | to be the only one able to reassign minors after the season begins | rosters are properly controlled. | As a/an League Admin, I want to be the only one able to reassign minors after the season begins, so that rosters are properly controlled.
A1 | Store Contact Info | * |  | Adult | to provide my basic contact information and my child’s information during registration | the league has accurate, protected minors’ data. | As a/an Adult, I want to provide my basic contact information and my child’s information during registration, so that the league has accurate, protected minors’ data.
L9 | Calendar display | 2 |  | League Admin | to have a calendar display | I can keep track of the date and times of the games in a season | As a/an League Admin, I want to have a calendar display, so that I can keep track of the date and times of the games in a season
L29 | Calendar matches | 2 |  | League Admin | to add/delete matches to calendar | I can show matches in a season for everyone to view | As a/an League Admin, I want to add/delete matches to calendar, so that I can show matches in a season for everyone to view
A10 | Calendar location | 1 |  | Adult | the calendar to show the location of the games | I can have quick directions to the game | As a/an Adult, I want the calendar to show the location of the games, so that I can have quick directions to the game
M11 | Previous Score | 1 |  | Team Manager | the calendar to show the score of previous games | I can quickly analyze team form | As a/an Team Manager, I want the calendar to show the score of previous games, so that I can quickly analyze team form
M12 | Practice Days | 1 |  | Team Manager | the calendar to allow me to add practice session | parents can know when we have practice | As a/an Team Manager, I want the calendar to allow me to add practice session, so that parents can know when we have practice
A13 | Notifications | 2 |  | Adult | the calendar to send me notifications | I can have a quick reminder when games are happening | As a/an Adult, I want the calendar to send me notifications, so that I can have a quick reminder when games are happening
L15 | Picture and Video feed | 3 |  | League Admin | A feed of pictures and videos from othe participating adults in the league | Registered adults as well as prospective parents can view special moments from the league | As a/an League Admin, I want A feed of pictures and videos from othe participating adults in the league, so that Registered adults as well as prospective parents can view special moments from the league
A16 | Comments on feed | 2 |  | Adult | To be able to comment/react on posts from other adults who posted on this app's feed of pictures and videos | Registered adults and interact with each other and other teams | As a/an Adult, I want To be able to comment/react on posts from other adults who posted on this app's feed of pictures and videos, so that Registered adults and interact with each other and other teams
L17 | Live match update | 5 |  | League Admin | A display for old and new matches that shows moves during a game and updates live for anyone to view on website | Anyone can be updated on live matches if they cannot attend and/or look at old matches | As a/an League Admin, I want A display for old and new matches that shows moves during a game and updates live for anyone to view on website, so that Anyone can be updated on live matches if they cannot attend and/or look at old matches
A18 | Match history | 1 |  | Adult | to be able to view the moves from old matches | I can review old games and help my player/child learn | As a/an Adult, I want to be able to view the moves from old matches, so that I can review old games and help my player/child learn
L19 | Live update input | 1 |  | League Admin | To be able to input moves from a game in real-time | I can provide real-time updates on a match | As a/an League Admin, I want To be able to input moves from a game in real-time, so that I can provide real-time updates on a match
L20 | Upload posts | 3 |  | Adult | To be able to upload picture/video posts as a registered adult | I can create community with other registered adults in the league | As a/an Adult, I want To be able to upload picture/video posts as a registered adult, so that I can create community with other registered adults in the league
E21 | Scoreboard (Live) | 1 |  | Guest, player, adult, team manager, or league admin | to know the events occurring throughout the game minute by minute (i.e. cards and goals) | so that I do not miss a moment of the match if I am not present | As a/an Guest, player, adult, team manager, or league admin, I want to know the events occurring throughout the game minute by minute (i.e. cards and goals), so that so that I do not miss a moment of the match if I am not present
E22 | future matches | *1 |  | Guest, player, adult, team manager, or league admin | to view the details of a future match (date, time, location, predicted weather) | so that I am able to help prepare for the stakes and intensity | As a/an Guest, player, adult, team manager, or league admin, I want to view the details of a future match (date, time, location, predicted weather), so that so that I am able to help prepare for the stakes and intensity
E23 | past matches | 1 |  | Guest, player, adult, team manager, or league admin | to view the details of a past match (date, time, location, weather, final score, cards)) | so that I can look back on previous matches, learn, and train accordingly for future matches | As a/an Guest, player, adult, team manager, or league admin, I want to view the details of a past match (date, time, location, weather, final score, cards)), so that so that I can look back on previous matches, learn, and train accordingly for future matches
E26 | Weather | 1 |  | Guest, player, adult, team manager, or league admin | to know the weather | so that I am properly prepared for said weather | As a/an Guest, player, adult, team manager, or league admin, I want to know the weather, so that so that I am properly prepared for said weather
L27 | Adult Approval | 1 |  | League Admin | to approve adults attempting to register/create an account | Only approved adults can register their children | As a/an League Admin, I want to approve adults attempting to register/create an account, so that Only approved adults can register their children
L28 | Add New Admin | 1 |  | League Admin | be able to add an additional league admin | Administration responsibilities can be split between multiple people | As a/an League Admin, I want be able to add an additional league admin, so that Administration responsibilities can be split between multiple people
A29 | Add Contact Info | * |  | Adult | to be able to add contact information to my profile for myself and my child | The team manager can contact me with any issues | As a/an Adult, I want to be able to add contact information to my profile for myself and my child, so that The team manager can contact me with any issues
M6 | manage a team | 2 |  | team manager | to be able to add or remove team players from my team | I can edit my team roster and finalize my team before my season starts | As a/an team manager, I want to be able to add or remove team players from my team, so that I can edit my team roster and finalize my team before my season starts
L30 | season start bracket | 1 |  | League Admin | to generate a random bracket of matches for the start of a season | Matches can be fairly decided at random | As a/an League Admin, I want to generate a random bracket of matches for the start of a season, so that Matches can be fairly decided at random
L31 | automated match decisions | 1 |  | League Admin | matches to be automatically created after the season begins based on scores of previous matches | Matches in the season are fairly decided based on who won and who lost | As a/an League Admin, I want matches to be automatically created after the season begins based on scores of previous matches, so that Matches in the season are fairly decided based on who won and who lost
L32 | playoff generation | 1 |  | League Admin | To automatically generate playoff matches based on previous match data | Playoff matches are fairly decided, and there isn't any accidental bias by manual decision | As a/an League Admin, I want To automatically generate playoff matches based on previous match data, so that Playoff matches are fairly decided, and there isn't any accidental bias by manual decision
L33 | Championship | 1 |  | League Admin | To automatically generate the championship based on previous match data | the championship is fairly decided and mark the end of a season | As a/an League Admin, I want To automatically generate the championship based on previous match data, so that the championship is fairly decided and mark the end of a season
Missing requirement: You have View Feed but no story allows someone to Upload Pic/Video to feed (unless A16 includes this, and in such case it is not properly written).
Missing requirement: I did not see a "react" to posts story nor did I see as a part of other stories like A16
Missing requirement: Playoffs generation. I did not see any story on playoffs generation.
Missing requirement: Season. Leagues usually have a season and a champion after a playoff.
note: added user stories are in blue
removed user stories are E23, E24 and combined into a new E22 and E23
Note on C3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5 points for a create is excessive. 2 more than enough, 3 if you want a complex interface.
Note on C4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Change the role of an user is just changing one simple field. 5 points is way too much. This is barely 1 point.
Note on C5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Create is just part of a crud. A team should not have many fields, I would say 1 is more than enough
Note on C7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The minor already have a profile on the system. Why sending an invite would be 5 points? That is about 1 point.
Note on C8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: A team invitation is a "Yes/No" check. Why that would be 5 points? That is barely 1 point.
Note on C10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: If this happens *during registration* then it is a part of A1 and not a separate story. Put it in the definition of done of A1.
Note on C12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The description of the story is vague. If the story is to only display a calendar then it is about 2-3 pts. If you are doing a full crud then about 8.
Note on F12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: What does "to have a calendar" mean in terms of software? Are you displaying a calendar? Full crud?
Note on C16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: If you already have a calendar display, why this is separate from calendar and why is it 3 points? Either this is a part of L9 or A10 or it should not be displayed with the calendar.
Note on C17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Why creating a new item on a calendar that you already have from L9 to M11, is 5 points? This is 1-2 tops.
Note on C18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8 points for a notification is excessive. And you did not specify how that notification will happen. An In-app message, SMS?
Note on C21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Display a feed is just a "read". The only complication are the multi-media elements (pics, videos).
Note on C29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Your story L17 is doing the heavy lifting on updating the live matches. Just displaying a live scoreboard is *not* worth 8 points. This is just a very simple display, 1 point.
Note on C30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: All these three stories (E22, E23, E24) are similar and seriously overestimated. If I look at a match I want to see every detail on the match: Location, type, date, etc. Creating multiple stories for each single detail is bad design.
Note on C36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This should be included when creating a profile/user.

## iteration 1
Calendar | L9 | L29 | L28
Admin | L2 | L7
Manager | M6 | M3 | M5
generate brackets | L30 | L31 | L32 | L33
Recording and displaying match data | E21 | E22 | E23 | E26

## Tasks
ID | Task Title | Task Description | Story ID

## Epics
ID | Epic Title | Description

## NFR
ID | Title | Category | Description | Affects
1 | Color Scheme | Visual / Design | The color scheme for the app should be *** | All
2 | Understand a NFR | Understandability | Simple example for the students to understand | Some
L14 | Visual Accessibility | Not a User Story. This is a NFR aftecting EVERY calendar-related story. |  | League Admin | the calendar to color-code the date of a game | there is some accessibility for visually impaired users | As a/an League Admin, I want the calendar to color-code the date of a game, so that there is some accessibility for visually impaired users
L20 | posts with minors protection | This is a NRF related to privacy |  | League Admin | All posted content with minors to be blurred for unregistered users | All minors will be protected even if posted publicly | As a/an League Admin, I want All posted content with minors to be blurred for unregistered users, so that All minors will be protected even if posted publicly
G30 | Guest Role | How is viewing a website 8 points? This is not a user story either, it is permission logic. Permission afects the *MOST* of the website. Things that affect ALL or MOST of the system are NFR |  | Guest | to be able to view the website without making an account or logging in | I am able to view the games even if I am not apart of the league | As a/an Guest, I want to be able to view the website without making an account or logging in, so that I am able to view the games even if I am not apart of the league
A4 | Responsibility Disclaimer | * |  | Adult | to see and accept a responsibility disclaimer when registering a minor | I can acknowledge accountability. | As a/an Adult, I want to see and accept a responsibility disclaimer when registering a minor, so that I can acknowledge accountability.
Note on C8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: How is viewing a website 8 points? This is not a user story either, it is permission logic. Permission afects the *MOST* of the website. Things that affect ALL or MOST of the system are NFR
Note on C9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Just displaying an disclaimer and clicking on agree is very simple. It is possible to do it without even need to code (which would be 0 points). This should be included on the denifition of done of registering kids.